## PPM_PROGRAM
Heures Estimées | [5 empty] | WEEKNO
Eq. No. | Desc. Equip. | Atelier | Metier | No. Tache | Desc. Tache | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | Total général
DIV0079 | EQUIPEMENTS GENERAUX DE LA LIGNE HYGIENIQUE 1 | SMECA | VIBRO | ICVER502 | VERIFIER FUITES AIR(AU SON)P1 AU COMPLET | WEEKNO 26: 8; WEEKNO 47: 8 | 16
DIV0362 | LASER #362 À LA TOOLROOM | SMECA | VIBRO | SCAL005 | CALIBRATION ET INSPECTION SYSTÈME LAZER | [53 empty] | 1 | bar: WEEKNO 20
F00-000-001 | ROUTES PM MULTI-LIGNES | SMECA | VIBRO | 020-0001 | TOURNÉE VIBRO | WEEKNO 4: 7.5; WEEKNO 8: 7.5; WEEKNO 12: 7.5; WEEKNO 16: 7.5; WEEKNO 20: 7.5; WEEKNO 24: 7.5; WEEKNO 28: 7.5; WEEKNO 32: 7.5; WEEKNO 36: 7.5; WEEKNO 40: 7.5; WEEKNO 44: 7.5; WEEKNO 48: 7.5; WEEKNO 52: 7.5 | 97.5
K00-000-001 | ROUTES PM MULTI-LIGNES | SMECA | VIBRO | 002-0091 | ANALYSE VIBRATION PKF "A" *DOC* | WEEKNO 4: 15.25; WEEKNO 8: 15.25; WEEKNO 12: 15.25; WEEKNO 16: 15.25; WEEKNO 20: 15.25; WEEKNO 24: 15.25; WEEKNO 28: 15.25; WEEKNO 32: 15.25; WEEKNO 36: 15.25; WEEKNO 40: 15.25; WEEKNO 44: 15.25; WEEKNO 48: 15.25; WEEKNO 52: 15.25 | 198.25
|  |  |  | 002-0092 | ANALYSE VIBRATION PKF "B" *DOC* | WEEKNO 7: 15.75; WEEKNO 14: 15.75; WEEKNO 23: 15.75; WEEKNO 31: 15.75; WEEKNO 39: 15.75; WEEKNO 47: 15.75 | 94.5
|  |  |  | 002-0094 | ANALYSE VIBRATION PKF TOIT *DOC* | WEEKNO 24: 2 | 2
MAC0012 | RECTIFIEUR CYLINDRIQUE | SMECA | VIBRO | SVER097 | VERIFIER BEARING DES MOTEURS | [53 empty] | 4 | bar: WEEKNO 1; WEEKNO 14; WEEKNO 28; WEEKNO 41
P00-000-001 | ROUTES PM MULTI-LIGNES | SMECA | VIBRO | SINS045I | TOURNEE VIBRO PLASTIQUE (ART) *DOC* | WEEKNO 4: 8; WEEKNO 8: 8; WEEKNO 12: 8; WEEKNO 16: 8; WEEKNO 20: 8; WEEKNO 24: 8; WEEKNO 28: 8; WEEKNO 32: 8; WEEKNO 36: 8; WEEKNO 40: 8; WEEKNO 44: 8; WEEKNO 48: 8; WEEKNO 52: 8 | 104
POM1153 | POMPE PARC SOLAIRE | SMECA | VIBRO | EINS004 | INSPECTION DE LA POMPE DU PARC SOLAIRE(VIBRATION) | [53 empty] | 4 | bar: WEEKNO 2; WEEKNO 15; WEEKNO 28; WEEKNO 42
ROU0911 | ROULEAU DEPLISSEUR (SPARE) ACELLI | SMECA | VIBRO | SINS045B | TOURNÉE MAINTENANCE PRÉDICTIVE VIBRO | [53 empty] | 12 | bar: WEEKNO 1; WEEKNO 5; WEEKNO 10; WEEKNO 14; WEEKNO 19; WEEKNO 23; WEEKNO 28; WEEKNO 32; WEEKNO 36; WEEKNO 41; WEEKNO 45; WEEKNO 50
TMPD004 | TOURNÉE VIBRATION | SMECA | VIBRO | SINS043 | TOURNÉE VIBRO NORAMPAC (B) | WEEKNO 3: 20; WEEKNO 11: 20; WEEKNO 19: 20; WEEKNO 27: 20; WEEKNO 35: 20; WEEKNO 43: 20; WEEKNO 51: 20 | 140
|  |  |  | SINS044A | TOURNEE #1 VIBRO NORAMPAC (A) *DOC* | WEEKNO 1: 40; WEEKNO 5: 40; WEEKNO 9: 40; WEEKNO 13: 40; WEEKNO 17: 40; WEEKNO 21: 40; WEEKNO 25: 40; WEEKNO 29: 40; WEEKNO 33: 40; WEEKNO 37: 40; WEEKNO 41: 40; WEEKNO 45: 40; WEEKNO 49: 40; WEEKNO 53: 40 | 560
|  |  |  | SINS044B | TOURNÉE #2 VIBRO NORAMPAC (A) | WEEKNO 2: 12; WEEKNO 6: 12; WEEKNO 10: 12; WEEKNO 14: 12; WEEKNO 18: 12; WEEKNO 22: 12; WEEKNO 26: 12; WEEKNO 30: 12; WEEKNO 34: 12; WEEKNO 38: 12; WEEKNO 42: 12; WEEKNO 46: 12; WEEKNO 50: 12 | 156
TMPD005 | TOURNÉE THERMOGRAPHIE | SMECA | VIBRO | DINS015 | INSPECTION THERMOGRAPHIQUE DES POMPES | WEEKNO 23: 2; WEEKNO 49: 2 | 4
TMPO001 | ENSEMBLE DES POMPES A FEU | SMECA | VIBRO | SINS078 | ANALYSE DE VIBRATION SUR L'ENSEMBLE DES POMPES À FEU | WEEKNO 3: 4; WEEKNO 7: 4; WEEKNO 12: 4; WEEKNO 16: 4; WEEKNO 20: 4; WEEKNO 25: 4; WEEKNO 29: 4; WEEKNO 34: 4; WEEKNO 38: 4; WEEKNO 42: 4; WEEKNO 47: 4; WEEKNO 51: 4 | 48
TMPT004 | TOURNÉE VIBRATION | SMECA | VIBRO | SINS045G | TOURNEE VIBRO TRAITEMENT DES EAUX *DOC* | WEEKNO 3: 12; WEEKNO 7: 12; WEEKNO 11: 12; WEEKNO 15: 12; WEEKNO 19: 12; WEEKNO 23: 12; WEEKNO 27: 12; WEEKNO 31: 12; WEEKNO 35: 12; WEEKNO 39: 12; WEEKNO 43: 12; WEEKNO 47: 12; WEEKNO 51: 12 | 156
TMPV100 | TOURNEE MAINTENANCE PREVENTIVE VIBRO LIC1 | SMECA | VIBRO | SINS045 | TOURNÉE MAINTENANCE PRÉDICTIVE VIBRO *DOC* | WEEKNO 1: 16; WEEKNO 5: 16; WEEKNO 9: 16; WEEKNO 13: 16; WEEKNO 17: 16; WEEKNO 21: 16; WEEKNO 25: 16; WEEKNO 29: 16; WEEKNO 33: 16; WEEKNO 37: 16; WEEKNO 41: 16; WEEKNO 45: 16; WEEKNO 49: 16; WEEKNO 53: 16 | 224
TMPV200 | TOURNEE MAINTENANCE PREVENTIVE VIBRO LIC2 | SMECA | VIBRO | SINS045A | TOURNÉE MAINTENANCE PRÉDICTIVE VIBRO *DOC* | WEEKNO 2: 16; WEEKNO 6: 16; WEEKNO 10: 16; WEEKNO 14: 16; WEEKNO 18: 16; WEEKNO 22: 16; WEEKNO 26: 16; WEEKNO 30: 16; WEEKNO 34: 16; WEEKNO 38: 16; WEEKNO 42: 16; WEEKNO 46: 16; WEEKNO 50: 16 | 208
TMPV300 | TOURNEE MAINTENANCE PREVENTIVE VIBRO LIC3 | SMECA | VIBRO | SINS045B | TOURNÉE MAINTENANCE PRÉDICTIVE VIBRO *DOC* | WEEKNO 3: 16; WEEKNO 7: 16; WEEKNO 11: 16; WEEKNO 15: 16; WEEKNO 19: 16; WEEKNO 23: 16; WEEKNO 27: 16; WEEKNO 31: 16; WEEKNO 35: 16; WEEKNO 39: 16; WEEKNO 43: 16; WEEKNO 47: 16; WEEKNO 51: 16 | 208
TMPV500 | TOURNEE MAINTENANCE PREVENTIVE VIBRO P1 | SMECA | VIBRO | SINS045C | TOURNÉE MAINTENANCE PRÉDICTIVE VIBRO *DOC* | WEEKNO 4: 4; WEEKNO 8: 4; WEEKNO 12: 4; WEEKNO 16: 4; WEEKNO 20: 4; WEEKNO 24: 4; WEEKNO 28: 4; WEEKNO 32: 4; WEEKNO 36: 4; WEEKNO 40: 4; WEEKNO 44: 4; WEEKNO 48: 4; WEEKNO 52: 4 | 52
TMPV700 | TOURNEE MAINTENANCE PREVENTIVE VIBRO DESEN | SMECA | VIBRO | SINS045D | TOURNÉE MAINTENANCE PRÉDICTIVE VIBRO *DOC* | WEEKNO 3: 8; WEEKNO 7: 8; WEEKNO 11: 8; WEEKNO 15: 8; WEEKNO 19: 8; WEEKNO 23: 8; WEEKNO 27: 8; WEEKNO 31: 8; WEEKNO 35: 8; WEEKNO 39: 8; WEEKNO 43: 8; WEEKNO 47: 8; WEEKNO 51: 8 | 104
TMPV800 | TOURNEE MAINTENANCE PREVENTIVE VIBRO P2 | SMECA | VIBRO | SINS045E | TOURNÉE MAINTENANCE PRÉDICTIVE VIBRO *DOC* | WEEKNO 4: 4; WEEKNO 8: 4; WEEKNO 12: 4; WEEKNO 16: 4; WEEKNO 20: 4; WEEKNO 24: 4; WEEKNO 28: 4; WEEKNO 32: 4; WEEKNO 36: 4; WEEKNO 40: 4; WEEKNO 44: 4; WEEKNO 48: 4; WEEKNO 52: 4 | 52
Total général | [5 empty] | 58 | 29 | 60 | 38.75 | 57 | 28 | 55.75 | 38.75 | 56 | 29 | 56 | 42.75 | 56 | 45.75 | 37 | 42.75 | 56 | 28 | 57 | 43.75 | 56 | 28 | 54.75 | 40.75 | 60 | 36 | 56 | 41.75 | 60 | 28 | 51.75 | 39.75 | 56 | 32 | 56 | 39.75 | 56 | 32 | 51.75 | 38.75 | 58 | 33 | 56 | 38.75 | 57 | 28 | 63.75 | 38.75 | 58 | 29 | 60 | 38.75 | 56 | 2445.25
Cette forme représente un segment. Les segments sont pris en charge dans Excel 2010 ou version ultérieure. En revanche, si la forme a été modifiée dans une version précédente d’Excel, ou si le classeur a été enregistré dans Excel 2003 ou une version précédente, vous ne pouvez pas utiliser le segment.
Cette forme représente un segment. Les segments sont pris en charge dans Excel 2010 ou version ultérieure. En revanche, si la forme a été modifiée dans une version précédente d’Excel, ou si le classeur a été enregistré dans Excel 2003 ou une version précédente, vous ne pouvez pas utiliser le segment.
Cette forme représente un segment. Les segments sont pris en charge dans Excel 2010 ou version ultérieure. En revanche, si la forme a été modifiée dans une version précédente d’Excel, ou si le classeur a été enregistré dans Excel 2003 ou une version précédente, vous ne pouvez pas utiliser le segment.
Cette forme représente un segment. Les segments sont pris en charge dans Excel 2010 ou version ultérieure. En revanche, si la forme a été modifiée dans une version précédente d’Excel, ou si le classeur a été enregistré dans Excel 2003 ou une version précédente, vous ne pouvez pas utiliser le segment.
Cette forme représente un segment. Les segments sont pris en charge dans Excel 2010 ou version ultérieure. En revanche, si la forme a été modifiée dans une version précédente d’Excel, ou si le classeur a été enregistré dans Excel 2003 ou une version précédente, vous ne pouvez pas utiliser le segment.
Cette forme représente un segment. Les segments sont pris en charge dans Excel 2010 ou version ultérieure. En revanche, si la forme a été modifiée dans une version précédente d’Excel, ou si le classeur a été enregistré dans Excel 2003 ou une version précédente, vous ne pouvez pas utiliser le segment.
Note on AL56: u038pbel: